## Sheet1
HARNEY COUNTY DEVELOPMENT DISTRICT PLANS DRAFT 4/6/22 | [10 empty] | CRT Comments
DISTRICT PLAN 1 BURNS: Community Gathering District
Objective 1.1: Invest in bike and pedestrian transportation network to attract private investment
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Improve Highway 20 streetscape from Egan to Broadway and along Broadway from Monroe to D Street. Partially completed |  | X | X | X | X | Enhance sidewalk and bike lane improvements to create a vibrant downtown. | City of Burns | County and ODOT, OTEC | ODOT, OTEC and City Tax Increment Financing (TIF)
B. Install bicycling related features, such as bike racks, wayfinding signs (perhaps public restrooms to encourage long distance cycling and hiking) |  |  | X | X | X | Enhance visitor experience. | Chamber of Commerce | City and County, GEODC | Travel Oregon, Main Street Grant, ODOT's Oregon Community Paths Grant program
partially completed |  | x | X | X | X | Improve pedestrian infrastructure and community appearance to foster investments in private housing. | City of Burns | School District, ODOT, (Safe Streets to School) County, GEODC, Hines | City Tax Increment Financing (TIF); County Community Development Block Grants (CDBG) ODOT's Oregon Community Paths Grant program
C. Integrate new residential development on the western edge of the city to connect to existing grid network and expand sidewalks and bike lanes to interconnect existing and new development. Actively starting |  | X | X | X | X | Integrate connections between new residential development with downtown to foster visitor access to downtown. | City of Burns | City of Burns Planning, OTEC, DLCD, County | Staff time to coordinate with future developers |  | SPWF-low cost financing to eligible municipalities for planning, design and construction of utilities and facilitites essential to industrial an dcommercial enterprise and job creation.
D. Enhance sidewalk connections south of Broadway and provide signage for connections to Harney Wildlife trailhead. 4-5 years down the road |  |  |  | X | X | Better leverage an asset that makes the the community distinct | City of Burns | County | City Tax Increment Financing (TIF); County Community Development Block Grants (CDBG) ODOT's Oregon Community Paths Grant program
E. Install graphic design traffic calming at Washington and Broadway intersection that builds off existing mural. |  | X |  |  |  | Encourage slower traffic to enhance pedestrian safety and add to vibrancy of downtown district. | Downtown Business Owners | City and ODOT | Main Street Grant, Travel Oregon,Eastern Oregon Visitors Association grant (focus changes annually), Ford Family-Good Neighbor grant (under $10,000) |  | Arts Build communities (ABC) Grant program provides $3-7K matching support
Objective 1.2: Target remote workers and tourism along Broadway
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Develop incentives such as off-setting rent for first few months and storefront improvements to attract new business. DONE |  |  | X |  |  | Have a tool that will attract new business URA | City of Burns | Downtown Business Owners | City Tax Increment Financing (TIF)
B16:18. Promote business opportunities and infill along Broadway with a detailed plan that documents available properties, businesses and potential incentives. Actively reach out to existing businesses in Bend, Baker City and Klamath Falls to consider expansion or promote on BizBuySell.com. |  |  | X | X | X | Actively build awareness of opportunities in downtown Burns | HCED | Downtown Business Owners; Chamber | Staff time
C. Continue to host events within downtown with community investment |  | x | X | X | X | Attract community members and visitors to also shop at local businesses | Downtown Businesses | Chamber, City of Burns | Volunteers, sponsorship, donations and fees
D. Encourage development of co-working space in Burns Paiute storefront that compliments cultural information. |  |  | X | X |  | Update: This space is for small Tribal owned businesses as well as a retail space for Tribal artisans to display and sell their wares. Refocus in 2022 | Burns Paiute Tribe | Downtown Business Owners, HCED, SBDC, HDP | Tribal Grants
E. Clarify and promote roles and services of entrepreneur services provided by HCED, SBDC, Burn Paiute tribe, Chamber and Spark. As a whole, this should be a strong suite of services to grow the small business and entrepreneur base. |  | X |  |  |  | Distinguish available services for small businesses vs. entrepreneurs to identify potential gaps and enhance marketing of programs | HCED | SBDC, HDP, Spark, Chamber, Burns Paiute Tribe | Staff time, SBDC, Business Oregon
F. Construct a welcome center or pocket park with information kiosks, picnic tables, education station, etc. |  |  |  | X |  | Enhance visitor experience | Chamber of Commerce | City of Burns, Downtown Businesses | Travel Oregon, Main Street Grant
Objective 1.3: Proactively engage in public-private partnerships to encourage quality development
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Implement urban renewal program similar to John Day to encourage remodeling of single-family homes considered brownfields. DONE |  | X | X | x | x | Improve housing stock within the community to serve potential employees and remote workers to foster economic development | City of Burns | County | City Tax Increment Financing (TIF); County ARPA funds
B. Build public infrastructure that encourages new residential development. Currently working on it, ORS 190 |  | X | X | X | X | Incentivitizes new housing development ORS 190, URA, New Legislation | City of Burns | County, R3 | City Tax Increment Financing (TIF); County ARPA funds
C. Encourage property owners to redevelop the two brownfield multi-family housing projects along Broadway at C and B Streets with a strategic RFP process to attract new investment. |  | X |  |  |  | Renovated properties with desired housing | HCED | Property Owners | Brownfield grant
D. Work with school district to actively promote and solicit development opportunities for Lincoln School |  | X |  |  |  | Attracts the highest and best use and developer to the property that aligns with value of quality development | HCED | Property Owners | Brownfield grant
E. Work with property owners at NE intersection of Broadway and Monroe and old post office to actively promote and solicit development opportunities |  | X |  |  |  | Attracts the highest and best use and developer to the property that aligns with value of quality development | HCED | Property Owners, new owner | Brownfield grant
DISTRICT 2 HINES: Business Opportunity District
Objective 2.1: Encourage New Natural Resource Economy (NNRE) production entrepreneurs
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Develop NNRE brand that supports traded sector businesses such as agriculture and renewable energy as opposed to a community focused brand. A brand for business can translate to communities but not vice-versa. |  | X |  |  |  | Enhance distinct brand for Harney County and help promote and market businesses | HDP | HCED, County, U of O professor and OSU professor who researched/wrote the NNRE report | USDA-Rural Energy Pilot Program Grant
B. Tell story of Harney County “incubator” space to encourage new entrepreneurs. Define intent of incubator and market. Determine available space on county property where Outlaw Furniture is located to recruit more production startups. Promote lease rates and terms to encourage new companies. |  |  | X |  |  | Encourage development of new NNRE production manufacturers | HCED | County, Agencies, USFS/multiple | Staff time
C. Work with OSU and OSU Extension to encourage biomass and precision agriculture technology innovation R&D in Harney County |  |  | X | X | X | Foster opportunity for new innovation and investment in Harney County | HCED | HDP, GEODC, USFS, Chuck | Staff time, Andrea, Feather, Chuck |  | Field trip to go see Chuck (ask Greg who Chuck is)
D. Continue to work with high schools to encourage opportunities in the NNRE economy through Career Technical Education (CTE) programs |  | X | X | X | X | Increase local job opportunities for youth to stay and invest in community | HCED | HDP, GEODC, TVCC, EOU | Staff time
E. Define infrastructure availability along Hotchkiss. Determine if new water or sewer needed to develop 69.5-acre brownfield parcel define size, length and cost. Secure environmental review of property. Promote and market the size with available infrastructure information. |  | X | X |  |  | Develop the necessary information to effectively market site | HCED | Property owner, City of Hines | Brownfield grant
Objective 2.2: Encourage electronic commerce industry
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Obtain Ecommerce District incentive from Business Oregon |  | X |  |  |  | Incentivizes and attracts new business opportunity | HCED | County; Cities and schools | Staff time |  | Art Fish Business Incentives Coord. E-Commerce Zone
B. Identify available warehouse space and lease rates and terms. Identify gaps. Work with developers or property owners to increase inventory if necessary. |  | X | X |  |  | Secure the necessary building infrastructure to support industry. | HCED | County; Cities and Hines | Staff time
C. Meet with other companies such as Oregon, Buy, Prep, Ship in Sisters to understand operation needs and how to provide them in Hines. |  | X | X |  |  | Ensure Hines has the necessary assets to attract new investment. Potentially develop leads for new businesses. | HCED | County; City of Hines | Staff time | ??
Objective 2.3: Allow for new housing types and encourage placemaking
Action |  | 1 yr | 2 yr | 3 yr | 4-5 yr | Action Outcome | Lead Org | Partners | Proposed Resource | Progress notes
A. Prepare a Master Plan for the central core to determine infill opportunities, enhance recreation amenities associated with trails, and define barriers to development. Explore changing commercial zone to mixed-use zone along central circle to allow for infill of homes such as townhouses but retains commercial use as well. Do not mandate ground-floor retail in a housing mixed-use project as it complicates construction and financing and increases risk of a project. |  | X | X |  |  | Remove barriers to develop and develop an intential vision and direction to enhance development in central core | City of Hines | County | Oregon DLCD, https://realtorparty.realtor/community-outreach/placemaking
B. Promote the 12.5 brownfield site and "ghost building" through an RFP process for new housing once necessary infrastructure is complete. |  | X |  |  |  | Attracts the highest and best use and developer to the property that aligns with value of quality development | HCED | City of Hines | Brownfield Grant |  | Karen Homilac-Brownfield Redevelopment Fund and Cleanup Fund
C. Build sidewalks to connect housing and central core of city. <Use safe routes to schools $ to capitalize on sidewalks serving multiple neighborhoods> |  |  | X | X |  | Improve pedestrian infrastructure and community appearance to foster investments in private housing. | City of Hines | County | Capital Improvement Funds; County Community Development Block Grants (CDBG), ODOT Safe Routes to School opens February 1
Comments Incorporated: | Pete Runnels, Harney County, Dan Brown-City of Burns, Kirby Letham- City of Hines, Greg Smith-HC Economic Development, Susan Christensen-GEODC, Tracy Kennedy-Burns Paiute Tribe